## Sheet1
[Project Name] Project Schedule
[Company Name]
| Project Lead: |  |  | Dale Torre
| Project Start Date: |  |  | 2018-02-09 | time axis 2018-02-05 to 2018-04-02
| Display Week: |  |  | 1 |  |  |  |  | 2018-02-05: Week 1; 2018-02-12: Week 2; 2018-02-19: Week 3; 2018-02-26: Week 4; 2018-03-05: Week 5; 2018-03-12: Week 6; 2018-03-19: Week 7; 2018-03-26: Week 8
[9 empty] | 2018-02-05 | [6 empty] | 2018-02-12 | [6 empty] | 2018-02-19 | [6 empty] | 2018-02-26 | [6 empty] | 2018-03-05 | [6 empty] | 2018-03-12 | [6 empty] | 2018-03-19 | [6 empty] | 2018-03-26
WBS | Task | Lead | Prede cessor | Start | End | Cal. Days | % Done | Work Days | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S
1 | Preparation | [Name]
1.1 | Study client & job specificities | [Name] |  | 2018-02-09 | 2018-02-12 | 4 | 100% | 0
1.2 | Appraisal of existing web site, IT systems |  |  | 2018-02-13 | 2018-02-17 | 5 | 0% | 0
1.3 | Check competition |  |  | 2018-02-18 | 2018-02-27 | 10 | 0% | 0
1.4 | Define site goals and overall strategy |  |  | 2015-03-25 | 2015-04-04 | 11 | 0% | 0
1.5 | Web design client questionnaire |  |  | 2015-04-05 | 2015-04-16 | 12 | 0% | 0
1
1.1 | Confirmation of site objectives (corporate, marketing, etc.) |  |  | 2018-02-09 | 2018-02-09 | 1 | 0% | 0
1.2 | Choose business model & Marketing plan |  |  | 2018-02-10 | 2018-02-10 | 1 | 0% | 0
1.3 | Plan interactions, technologies & functionalities |  |  | 2018-02-11 | 2018-02-11 | 1 | 0% | 0
1.4 | Choose content management system |  |  | 2018-02-12 | 2018-02-12 | 1 | 0% | 0
1.5 | Choose data delivery model and backup |  |  | 2018-02-13 | 2018-02-13 | 1 | 0% | 0
1.6 | Roles and responsibilities |  |  | 2018-02-14 | 2018-02-14 | 1 | 0% | 0
1.7 | Initial timetable |  |  | 2018-02-15 | 2018-02-15 | 1 | 0% | 0
1.8 | Quote submission |  |  | 2018-02-16 | 2018-02-16 | 1 | 0% | 0
1.9 | Project validation & deposit paid |  |  | 2018-02-17 | 2018-02-17 | 1 | 0% | 0
1 | Planning
1.1 | Website title |  |  | 2018-02-09 | 2018-02-09 | 1 | 0% | 0
1.2 | Host selection & registration |  |  | 2018-02-10 | 2018-02-10 | 1 | 0% | 0
1.3 | Domain name selection & registration |  |  | 2018-02-11 | 2018-02-11 | 1 | 0% | 0
1.4 | Mirrors & other domain-related registrations |  |  | 2018-02-12 | 2018-02-12 | 1 | 0% | 0
1.5 | Website structure & information architecture |  |  | 2018-02-13 | 2018-02-13 | 1 | 0% | 0
1.6 | Validate wireframe |  |  | 2018-02-14 | 2018-02-14 | 1 | 0% | 0
1 | [Task Category]
I
1 | [Task Category]
1.1 | [Task] |  |  | 2018-02-09 | 2018-02-09 | 1 | 0% | 0
1.2 | [Task] |  |  | 2018-02-10 | 2018-02-10 | 1 | 0% | 0
1.3 | [Task] |  |  | 2018-02-11 | 2018-02-11 | 1 | 0% | 0
1.4 | [Task] |  |  | 2018-02-12 | 2018-02-12 | 1 | 0% | 0
1.5 | [Insert Rows above this one, then Hide or Delete this row]
Note on A7: Work Breakdown Structure Level 1: 1, 2, 3, ... Level 2: 1.1, 1.2, 1.3, ... Level 3: 1.1.1, 1.1.2, 1.1.3, … The WBS uses a formula to control the numbering, but the formulas are different for different levels.
Note on B7: Task Enter the name of each task and sub-task. Use indents for sub-tasks.
Note on C7: Task Lead Enter the name of the Task Lead in this column.
Note on D7: Predecessor Tasks: You can use this column to enter the WBS of a predecessor for reference. The PRO version includes template rows that allow you to automatically calculate the Start Date based on the Predecessor.
Note on E7: Task Start Date You can manually enter the Start Date for each task or use a formula to create a dependency on a Predecessor. For example, you could enter =enddate+1 to set the Start date to the next calendar day, or =WORKDAY(enddate,1) to set the Start date to the next work day (excluding weekends), where enddate is the cell reference for the End date of the Predecessor task.
Note on G7: Duration (Calendar Days) The duration is the number of calendar days for the given task. The duration is calculated as the End Date minus the Start Date plus 1 day, so that a task starting and ending on the same day has a duration of 1 day. Note: The conditional formatting used to create the gantt chart references this column.
Note on H7: Percent Complete Update the status of this task by entering the percent complete (between 0% and 100%).
Note on I7: Work Days Counts the number of work days, excluding the weekends (Saturday and Sunday). In the PRO version, you can customize the work week and list specific non-working days like holidays. In the PRO version, the default input is the Work Days instead of the Calendar Days.